## Lighthouse Input form
Name | Email | Project Type | Project Name | Phase | Milestone | Process | Lifecycle | Function | Department | Title | Best Practice or Issue | Description | Proposed Root Cause | Proposed Recommendation | Key Words | Impact Category | Impact Level | Type | Project Number | Phase others | Milestone others | Project Name others | IVD Project Name | Low Risk Project Name | IA/EUA Milestone | IVD Milestone | Low Risk Milestone | Product Care Project Milestone | Standalone Software Milestone | IA/EUA Ph | IVD PH | Low Risk PH | Product Care Project PH | Standalone Software PH
Heiko Burgard | heiko.burgard@roche.com | IVD | Smarticles vivoDx System | Routine Manufacturing and Sales | Milestone LD |  | Smarticles | Global Operations | Production (Bulk, Fill, Package, Central Weigh) | Mixed Bag | Issue | #NAME? | #NAME? | #NAME? | vivoDx, instrument, ops, smarticles | Quality/Compliance/Product Safety | Medium | Project | [5 empty] | shotgunPETE |  |  | Milestone DI |  |  |  |  | Development Phase
Jennifer Griswold | jennifer.griswold@roche.com | IVD | Smarticles vivoDx System | Development Phase | Milestone DO |  | Smarticles | Finance/Project Management Office | Assay | Initial stability before DI | Issue | Initial stability assessment before DI | REACH Substrate - Stability was not assessed in final form before formulation lock due to timeline constraints. which could limit some of the customer base. | Assess stability in final form using real-time and accelerated conditions with a draft test method before finalizing the formulation/prior to DI. | Stability | Schedule/Time | High | Project |  |  |  |  | TaqScreen MPX v2 Dual Target |  |  | Milestone DG |  |  |  |  | Feasibility Phase
Jennifer Griswold | jennifer.griswold@roche.com | IVD | Smarticles vivoDx System | Development Phase | Milestone DO |  | Smarticles | Research & Development | Assay | Smarticles manufacturing optimization post DI | Issue | The Smarticles fermentation process was "optimized" post DI. The PL process was different from the VL process (including fermentation temperature, oxygen settings). | Official stability and TPVs were completed with PL process Smarticles, which were stable (up to 23 Months). | I'm not quite sure what the right recommendation is here - potential options: 1) Assess if a change is an "optimization" or a "process change" 2) Assess stability on VL material prior to DO/LD if there's a change from PL to VL | Stability, post-DI optimization, equivalency | Quality/Compliance/Product Safety | High | Process Improvement
Robert Current | robert_b.current@roche.com | IVD | Smarticles vivoDx System | Feasibility Phase | Milestone DG |  | Smarticles | Research & Development | Assay | Have Control of your Process and Components | Best Practice | 1. The Smarticles assays, the Smarticles themselves were native phages and not custom designed for the target organisms. |  | 1. Take the time and hire the experts necessary to understand and custom design phages to specific targets. As a subset of this, have a better understanding of what the target on the MRSA | Process, Components, Planning | Quality/Compliance/Product Safety | High | Process Improvement