## Lighthouse Input form
Name | Email | Project Type | Project Name | Phase | Milestone | Process | Lifecycle | Function | Department | Title | Best Practice or Issue | Description | Proposed Root Cause | Proposed Recommendation | Key Words | Impact Category | Impact Level | Type | Project Number | Phase others | Milestone others | Project Name others | IVD Project Name | Low Risk Project Name | IA/EUA Milestone | IVD Milestone | Low Risk Milestone | Product Care Project Milestone | Standalone Software Milestone | IA/EUA Ph | IVD PH | Low Risk PH | Product Care Project PH | Standalone Software PH
Heiko Burgard | heiko.burgard@roche.com | IVD | Smarticles vivoDx System | Routine Manufacturing and Sales | Milestone LD |  | Smarticles | Global Operations | Production (Bulk, Fill, Package, Central Weigh) | Mixed Bag | Issue | #NAME? | #NAME? | #NAME? | vivoDx, instrument, ops, smarticles | Quality/Compliance/Product Safety | Medium | Project | [5 empty] | shotgunPETE |  |  | Milestone DI |  |  |  |  | Development Phase
Jennifer Griswold | jennifer.griswold@roche.com | IVD | Smarticles vivoDx System | Development Phase | Milestone DO |  | Smarticles | Finance/Project Management Office | Assay | Initial stability before DI | Issue | Initial stability assessment before DI | REACH Substrate - Stability was not assessed in final form before formulation lock due to timeline constraints. which could limit some of the customer base. | Assess stability in final form using real-time and accelerated conditions with a draft test method before finalizing the formulation/prior to DI. | Stability | Schedule/Time | High | Project |  |  |  |  | TaqScreen MPX v2 Dual Target |  |  | Milestone DG |  |  |  |  | Feasibility Phase
Jennifer Griswold | jennifer.griswold@roche.com | IVD | Smarticles vivoDx System | Development Phase | Milestone DO |  | Smarticles | Research & Development | Assay | Smarticles manufacturing optimization post DI | Issue | The Smarticles fermentation process was "optimized" post DI. The PL process was different from the VL process (including fermentation temperature, oxygen settings). | Official stability and TPVs were completed with PL process Smarticles, which were stable (up to 23 Months). | I'm not quite sure what the right recommendation is here - potential options: 1) Assess if a change is an "optimization" or a "process change" 2) Assess stability on VL material prior to DO/LD if there's a change from PL to VL 3) Finalize fermentation process before PLs are produced? | Stability, post-DI optimization, equivalency | Quality/Compliance/Product Safety | High | Process Improvement
Robert Current | robert_b.current@roche.com | IVD | Smarticles vivoDx System | Feasibility Phase | Milestone DG |  | Smarticles | Research & Development | Assay | Have Control of your Process and Components | Best Practice | 1. The Smarticles assays, the Smarticles themselves were native phages and not custom designed for the target organisms. |  | 1. Take the time and hire the experts necessary to understand and custom design phages to specific targets. As a subset of this, have a better understanding of what the target on the MRSA is. (specific Protein, carbohydrate, etc) If you don't have an understanding of what the phage is binding to, you can't cross check the existence of the target on other organisms. | Process, Components, Planning | Quality/Compliance/Product Safety | High | Process Improvement